{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":32,"n_cols":17,"rows_kept":32,"merged":[[1,0,1,16],[2,0,2,1],[2,2,2,4],[2,5,2,7],[2,8,2,10],[2,11,2,13],[2,14,2,16],[3,0,3,1],[3,2,3,4],[3,5,3,7],[3,8,3,10],[3,11,3,13],[3,14,3,16],[4,0,4,1],[5,0,7,0],[6,1,7,1],[6,4,7,4],[6,7,7,7],[6,10,7,10],[6,13,7,13],[6,16,7,16],[8,0,19,0],[8,1,10,1],[11,1,18,1],[19,2,19,3],[19,5,19,6],[19,8,19,9],[19,11,19,12],[19,14,19,15],[20,0,28,0],[20,1,22,1],[23,1,27,1],[28,2,28,3],[28,5,28,6],[28,8,28,9],[28,11,28,12],[28,14,28,15],[29,0,29,1],[29,2,29,4],[29,5,29,7],[29,8,29,10],[29,11,29,13],[29,14,29,16],[30,0,30,1],[30,2,30,16],[31,0,31,1],[31,2,31,16]],"flags":["formulas_cached_only"]}
["附件"]
["山东省工程建设项目建筑师负责制后评估评分表"]
["评价阶段",null,"前期策划",null,null,"工程设计",null,null,"招标采购",null,null,"施工监督",null,null,"运营维护"]
["评价时间",null,"取得建设工程规划许可证后一个月内",null,null,"取得建设工程施工许可证后两个月内",null,null,"取得验收合格证后两个月内",null,null,"取得验收合格证后三个月内",null,null,"投入运营满一年后的两个月内"]
["评价体系",null,"编号","内容","分值","编号","内容","分值","编号","内容","分值","编号","内容","分值","编号","内容","分值"]
["控制项","建设单位","A1.1","取得建设工程规划许可证","/","A2.1","取得建设工程施工许可证","/","A3.1","取得竣工验收合格证","/","A4.1","取得竣工验收合格证","/","A5.1","投入使用满一年","/"]
[null,"建筑师","A1.2","签署建筑师告知承诺书","/","A2.2","签署建筑师告知承诺书","/","A3.2","完成专业顾问招标","/","A4.2","签署所有竣工验收需建筑师签署的文件","/",null,null,"/"]
[{"$nulls":5},"A2.3","完成专项评审、论证",null,"A3.3","施工相关合同附图",null,"A4.3","签署五方责任书"]
["基础项","建设单位","B1.1","给予建筑师合理工期",10,"B2.1","给予建筑师合理工期",10,"B3.1","给予建筑师合理工期",5,"B4.1","给予建筑师合理工期",5]
[null,null,"B1.2","拆改更新由原建筑师承担",5,"B2.2","设计总包",20,{"$nulls":3},"B4.2","授权建筑师签发施工指令",10]
[]
[null,"建筑师","B1.3","项目建议书",10,"B2.3","责任建筑师技术总控",30,"B3.2","参与施工招标",15,"B4.3","项目计划及会议管理",10,"B5.1","运营前配合",15]
[null,null,"B1.4","可行性研究报告",10,"B2.4","设计咨询进度管控",20,"B3.3","定板定样",10,"B4.4","施工质量、进度监督",30,"B5.2","监督缺陷整改",10]
[null,null,"B1.5","城市设计",10,"B2.5","设计任务书",10,"B3.4","合同管理",10,"B4.5","变更管理",10,"B5.3","监督评估和保修期检查",5]
[null,null,"B1.6","建筑策划",5,"B2.6","设计成果完整性",10,"B3.5","建筑师团队廉洁性",10,"B4.6","造价控制",20]
[{"$nulls":6},"专项设计咨询顾问采购",10,{"$nulls":3},"B4.7","分部分项及竣工验收",20]
[{"$nulls":6},"建筑师团队稳定性",10,{"$nulls":3},"B4.8","驻场和巡场",15]
[{"$nulls":11},"B4.9","建筑师团队廉洁性",10]
[{"$nulls":11},"B4.10","建筑师团队稳定性",10]
[null,null,"基础项得分小计",null,50,"基础项得分小计",null,120,"基础项得分小计",null,50,"基础项得分小计",null,140,"基础项得分小计",null,30]
["评价项","建设单位","C1.1","建筑师有合理的服务取费并及时支付",10,"C2.1","建筑师有合理的服务取费并及时支付",10,"C3.1","建筑师有合理的服务取费并及时支付",10,"C4.1","建筑师有合理的服务取费并及时支付",10]
[null,null,"C1.2","授权建筑师开展专项咨询和评估",10,{"$nulls":3},"C3.2","授权建筑师参与技术评标",10,"C4.2","授权建筑师参与进度款签批",10]
[]
[null,"建筑师","C1.3","行政审批",5,"C2.2","开展相关专项设计咨询",20,"C3.3","参与标段及界面划分",5,"C4.3","建筑师服务延伸",15,"C5.1","项目获奖与论文",15]
[null,null,"C1.4","控制性详细规划设计",5,"C3.3","报批报建",10,"C3.4","采购考察",5,"C4.4","报批报建",10,"C5.2","工程总结与质保金审核",10]
[{"$nulls":5},"C2.3","建设方对建筑师服务的阶段性评价",10,{"$nulls":3},"C4.5","建设方对建筑师服务的总体评价",10,"C5.3","提供使用手册和培训",5]
[{"$nulls":5},"C3.4","责任建筑师项目负担",5,{"$nulls":4},"对政府允许的分项出具专项验收意见",5]
[{"$nulls":5},"C2.4","投保相关保险",5]
[null,null,"评价项得分小计",null,30,"评价项得分小计",null,60,"评价项得分小计",null,30,"评价项得分小计",null,60,"评价项得分小计",null,30]
["各阶段总分",null,80,null,null,180,null,null,80,null,null,200,null,null,60]
["加分项",null,50]
["评价总分",null,650]